## twoplugs_report
TestCase ID | Headline | Status | Date Ran | Defect ID_Jira | Severity | Defect Status
TP_001 | Landing Page Features | passed | 19/12/2019
TP_002 | Landing page > "JOIN NOW FOR FREE" button –– Sign Up page | failed | 19/12/2019 | T1-14 | 3 | open
TP_003 | Functionality of "LIVE POSTING " Link | passed | 19/12/2019
TP_004 | LIVE POSTING >Need | passed | 19/12/2019
TP_005 | LIVE POSTINGS > Service | passd | 19/12/2019
TP_006 | LIVE POSTINGS > "Buy", "Sell", "Bid" buttons | skip | 19/12/2019
TP_007 | LIVE POSTINGS > Drop down icons | skip | 19/12/2019
TP_008 | LIVE POSTINGS > Filter Button | skip | 19/12/2019
TP_009 | LIVE POSTINGS > Show Advance Filter Link | skip | 19/12/2019
TP_010 | LIVE POSTINGS > Search Result Display | passed | 19/12/2019
TP_011 | Functionality of "Lets Go" Button | passed | 19/12/2019
TP_012 | LIVE POSTINGS > Category> Search | passed | 19/12/2019
TP_013 | LIVE POSTINGS >Location and Distance>Search | passed | 19/12/2019
TP_014 | Landing page > CONTACT | passed | 19/12/2019
TP_015 | Landing page > twoPLUGS Logo | passed | 19/12/2019
TP_016 | Landing page > Video –– link | passed | 19/12/2019
TP_017 | Landing page > video > Share link > Social Media Links | passed | 20/12/2019
TP_018 | Landing page > TESTIMONIAL IMAGES – CLICKABLE | failed | 20/12/2019 | T1-13 | 3 | open
TP_019 | Landing page > Frequently Asked Questions > drop down Buttons | passed | 20/12/2019
TP_020 | Facebook, Twitter, and Instagram –– Links | passed | 20/12/2019
TP_021 | Landing Page > Footer and bottom buttons/links | passed | 20/12/2019
TP_022 | Sign Up page > Valid Data in all columns | passed | 20/12/2019
TP_023 | Sign Up page > Invalid User Name > Special Characters | passed | 20/12/2019
TP_024 | Sign Up page > Invalid User Name > Character length less than 2 or more than 15 or Blank username | passed | 20/12/2019
TP_025 | Sign Up page > Invalid Email | passed | 20/12/2019
TP_026 | Sign Up page > Password (Negative) | passed | 20/12/2019
TP_027 | Sign Up page > Password (Negative) | passed | 20/12/2019
TP_028 | Sign Up page > Password (Negative) | passed | 20/12/2019
TP_029 | Sign Up page > Password – Criteria (Negative) | passed | 20/12/2019
TP_030 | Sign Up page > Password – Criteria (Negative) | passed | 20/12/2019
TP_031 | Sign Up page > Password – Criteria (Negative) | passed | 20/12/2019
TP_032 | Sign Up page > Password – Criteria (Negative) | passed | 20/12/2019
TP_033 | Login Page > Valid Email / username & password | passed | 20/12/2019
TP_034 | Login Page > Invalid Email / username & Valid Password | failed | 20/12/2019 |  | 3 | closed
TP_035 | Login Page > Forgot Password/Reset Password (+) and Page New Design | skip | 20/12/2019
TP_036 | Login Page > Reset Password (-) | skip | 20/12/2019
TP_037 | Login Page > Password Reset Link (+) and New Design | skip | 20/12/2019
TP_038 | Login Page > Password Reset Link (-) | skip | 20/12/2019
TP_039 | Sign Up – Button – 50 eeds | skip | 20/12/2019
TP_040 | Home Page > Quick tour video | skip | 20/12/2019
TP_041 | Login Page > Valid Email / username & Invalid Password | passed | 20/12/2019
TP_042 | Home Page > Highlighted Menu tab in Menu bar | passed | 20/12/2019
TP_043 | Home page > Dash Board updates > All Tables Headers | passed | 20/12/2019
TP_044 | Home page > Dash Board updates > Transactions> "MORE" buttons | failed | 20/12/2019 | T1_19 | 3 | open
TP_045 | Home page > Dash Board updates > Live update from users I follow > "MORE" buttons | failed | 20/12/2019 | T1_20 | 3 | open
TP_046 | Home page > Dash Board updates > Live update in my Network > "MORE" buttons | failed | 20/12/2019 | T1_21 | 3 | open
TP_047 | Admin > Transaction History Feature | skip | 21/12/2019
TP_048 | Admin > Transaction History – "Email address/Username" box (positive) | skip | 21/12/2019
TP_049 | Admin > Transaction History – "Email address/Username" box (Negative) | skip | 21/12/2019
TP_050 | Admin > Complaint Trail | skip | 21/12/2019
TP_051 | Admin > Message Trail | skip | 21/12/2019
TP_052 | Admin > security checks to protect eeds (Positive) | skip | 21/12/2019
TP_053 | Admin > security checks to protect eeds (Negative) | skip | 21/12/2019
TP_054 | Admin > Document File Format (Positive) | skip | 21/12/2019
TP_055 | Admin > Document File Format (Negative) | skip | 21/12/2019
TP_056 | Admin > Uploaded Document – Edit | skip | 21/12/2019
TP_057 | Admin > Uploaded Document – delete | skip | 21/12/2019
TP_058 | Plugs Page > Search Box – "Search for Service or Need"(Positive) | passed | 22/12/2019
TP_059 | Plugs Page > Search Box – "Search for Service or Need"(Negative) | passed | 22/12/2019
TP_060 | Plugs Page > search suggestion List (Positive) | passed | 22/12/2019
TP_061 | Plugs Page > search suggestion List (Negative) | passed | 22/12/2019
TP_062 | Plugs Page > Search Box – "All" | passed | 22/12/2019
TP_063 | Plugs Page > Location – Advanced Filters Dropdown list | skip | 22/12/2019
TP_064 | Plugs Page > Add, Edit --Date and Time | passed | 22/12/2019
TP_065 | Plugs Page > 'SORT BY PRICE" – Drop Down Icon | passed | 22/12/2019
TP_066 | Plugs Page > 'SORT BY Names" – Drop Down Icon | failed | 22/12/2019 | T1_71 | 3 | open
TP_067 | Plugs Page > 'SORT BY RATINGS" – Drop Down Icon | passed | 22/12/2019
TP_068 | Plugs Page > 'SORT BY Recently Updated" – Drop Down Icon | passed | 22/12/2019
TP_069 | Services – Bidding workflow–'Posting Services | passed | 22/12/2019
TP_070 | Services – Bidding workflow – Bid button | passed | 22/12/2019
TP_071 | Services – Bidding workflow – Send (Buyer Side) | passed | 22/12/2019
TP_072 | Services – Bidding workflow – Cancel (Buyer Side) | passed | 22/12/2019
TP_073 | Services – Bidding – Price with Negative value (-) or Zero or blank or alphabets or special characters | failed | 22/12/2019 | T1_72 | 4 | open
TP_074 | Services – Bidding -Sale Agreement not checked (Negative) | passed | 22/12/2019
TP_075 | Services - Bidding Workflow - Lets Negotiate - Decline | passed | 22/12/2019
TP_076 | Services - Bidding Workflow - Lets Negotiate - Accept | passed | 22/12/2019
TP_077 | Services - Bidding Workflow - Lets Negotiate - Make an offer | passed | 22/12/2019
TP_078 | Services - No Bidding workflow - I want this | passed | 22/12/2019
TP_079 | Services - No Bidding workflow - I want this > Deny Purchase | passed | 22/12/2019
TP_080 | Services - No Bidding workflow - I want this > Accept | passed | 22/12/2019
TP_081 | Need Bidding" pop up – New Design | skip | 22/12/2019
TP_082 | Needs - Bidding workflow - Posting Needs | passed | 22/12/2019
TP_083 | Needs - Bidding workflow > Send | passed | 22/12/2019
TP_084 | Needs - Bidding workflow > Cancel | passed | 22/12/2019
TP_085 | Need – Bidding – Price with Negative value (-) or special characters or alphabets | passed | 22/12/2019
TP_086 | Needs - Bidding > Decline Bid | passed | 22/12/2019
TP_087 | Needs - Bidding > Make an Offer | passed | 22/12/2019
TP_088 | Needs - Bidding > Accept | passed | 22/12/2019
TP_089 | Need detail page > "Share Service" icons | passed | 22/12/2019
TP_090 | Service detail page > "Share Service" icons | passed | 22/12/2019
TP_091 | Service/Need detail page > "Share Service" icons > Facebook | passed | 22/12/2019
TP_092 | Service/Need detail page > "Share Service" icons > Twitter | passed | 22/12/2019
TP_093 | Service/Need detail page > "Share Service" icons >Mail | skip | 22/12/2019
TP_094 | Transaction History Page > Complaint-icon | passed | 22/12/2019
TP_095 | Transaction History Page > Refund – icon (Positive) | passed | 22/12/2019
TP_096 | Transaction History Page > Refund icon – Invalid | passed | 22/12/2019
TP_097 | Menu bar > Messages > Message icon | passed | 22/12/2019
TP_098 | Transaction History Page > Transactions Legend | passed | 22/12/2019
TP_099 | Messages > Messages in each page | passed | 22/12/2019
TP_100 | Messages > Sort by > drop down list | passed | 22/12/2019
TP_101 | Profile page > Display time AM/PM (EST) | passed | 22/12/2019
TP_102 | Profile page > Follow | passed | 22/12/2019
TP_103 | Profile page > Unfollow | passed | 22/12/2019
TP_104 |  | passed | 22/12/2019
TP_105 | Profile page > Transfer EEDS icon(Negative) | passed | 23/12/2019
TP_106 | Profile page > Message | passed | 23/12/2019
TP_107 | Profile page > Report | passed | 23/12/2019
TP_108 | Menu bar > Hi User – Dropdown Menu list | passed | 23/12/2019
TP_109 | Profile Page > Following | passed | 23/12/2019
TP_110 | Profile page > Followers | passed | 23/12/2019
TP_111 | Profile page > Experience Level– Rating Stars | skip | 23/12/2019
TP_112 | Profile page > SERVICE SOLD | passed | 23/12/2019
TP_113 | Profile page > SERVICE BOUGHT | passed | 23/12/2019
TP_114 | Profile page > TOTAL BALANCE | passed | 23/12/2019
TP_115 | Profile page > Edit Page link | passed | 23/12/2019
TP_116 | Profile page > Profile Table/Box | passed | 23/12/2019
TP_117 | Profile page > About Table/Box | skip | 23/12/2019
TP_118 | Profile page > NEEDS and Services Boxes/Tables | passed | 23/12/2019
TP_119 | "Need / Service Details" page – Review | passed | 23/12/2019
TP_120 | Create/Add/Edit – Service | passed | 23/12/2019
TP_121 | Create/Add/Edit – Need | passed | 23/12/2019
TP_122 | Add/Edit- Need/Service page> Select a Category (Positive) | passed | 23/12/2019
TP_123 | Add/Edit- Need/Service page> Not Select a Category (Negative) | passed | 23/12/2019
TP_124 | Add/Edit- Need/Service page> Sub-category | passed | 23/12/2019
TP_125 | Add/Edit- Need/Service page> Price(Positive) | passed | 23/12/2019
TP_126 | Add/Edit- Need/Service page> Price(Negative) | passed | 23/12/2019
TP_127 | Add/Edit- Service page> Refund – Validity (Positive) | passed | 23/12/2019
TP_128 | Add/Edit- Service page> Refund – Validity (Negative) | passed | 23/12/2019
TP_129 | Add/Edit- Need/Service page> Video URL –– YouTube (Positive) | passed | 23/12/2019
TP_130 | Add/Edit- Need/Service page> Video URL (Negative) | passed | 23/12/2019
TP_131 | Add/Edit- Need/Service page> Video URL – Delete | passed | 23/12/2019
TP_132 | Add/Edit- Service page> Refund % –- ? | passed | 23/12/2019
TP_133 | Add/Edit- Need/Service page> Deposit –-? | skip | 23/12/2019
TP_134 | Add/Edit- Need/Service page> Payment Type –– ? | passed | 23/12/2019
TP_135 | Edit services | passed | 23/12/2019
TP_136 | Edit Needs | passed | 23/12/2019
TP_137 | Services_active status | passed | 23/12/2019
TP_138 | Services_inactive status | passed | 23/12/2019
TP_139 | Needs_active status | passed | 23/12/2019
TP_140 | Needs_inactive status | passed | 23/12/2019
TP_141 | Needs table_number of active needs | passed | 23/12/2019
TP_142 | Services table_number of active services | passed | 23/12/2019
TP_143 | New Need_no bidding allowed | passed | 23/12/2019
TP_144 | Edit Need_no bidding allowed | passed | 23/12/2019
TP_145 | New service_no bidding allowed | passed | 23/12/2019
TP_146 | Edit Service_no bidding allowed | passed | 23/12/2019
TP_147 | Add profile picture_positive | passed | 23/12/2019
TP_148 | Add profile picture_negative | passed | 23/12/2019
TP_149 | Add bio picture_positive | passed | 23/12/2019
TP_150 | Add bio picture_negative | passed | 23/12/2019
TP_151 | Profile picture_crop image | passed | 23/12/2019
TP_152 | User_password change_positive | passed | 23/12/2019
TP_153 | User_password change_negative (Only alphabets / Numbers / Less than 8 characters / Same as old password) | passed | 23/12/2019
TP_154 | User_Email change | passed | 23/12/2019
TP_155 | User_Email change_negative (Enter without '@' or '.') | passed | 23/12/2019
TP_156 | User_signout | passed | 23/12/2019
TP_157 | User_Idle –- 1 Hour (+) | passed | 23/12/2019
TP_158 | User_feedback | passed | 23/12/2019
TP_159 | Support_support center topics | passed | 23/12/2019
TP_160 | Terms of use_terms of use page | passed | 23/12/2019
TP_161 | Privacy policy_privacy policy page | passed | 23/12/2019
TP_162 | Security | passed | 23/12/2019
TP_163 | Sign up_sign up with facebook | passed | 23/12/2019
TP_164 | Sign in_sign in with facebook | passed | 23/12/2019
TP_165 | Profile page > Add Gender (M or F) | passed | 23/12/2019
TP_166 | Notification emails_matching service or nedds are added to the same network | passed | 23/12/2019
TP_167 | Sign up with facebook_referral link | skip | 23/12/2019
TP_168 | Setting_refer a friend functionality | passed | 23/12/2019
TP_169 | Settings_posting referral link on FB | passed | 23/12/2019
TP_170 | Settings_posting referral link on Twitter | passed | 23/12/2019
TP_171 | Referred user_Sign up | passed | 23/12/2019
TP_172 | Referred user_Sending Referral email link to Twoplugs users (Negative) | passed | 23/12/2019
TP_173 | Referred link on facebook_sign up page | passed | 23/12/2019
TP_174 | Referral link of Twitter_sign up page | passed | 23/12/2019
TP_175 | Sign up_send emails to non activated accounts | skip | 23/12/2019
TP_176 | Sign up with facebook_email to redeem 50 eeds | skip | 23/12/2019
TP_177 | Active user_send email when balance is 0 eeds | skip | 23/12/2019
TP_178 | Service title_50 characters | passed | 23/12/2019
TP_179 | Need title_50 characters | passed | 23/12/2019
TP_180 | Service Description_Allowing service description only upto 256 characters | passed | 23/12/2019
TP_181 | Need Description_Allowing need description only upto 256 characters | passed | 23/12/2019
TP_182 | Transaction table_Eeds received | passed | 23/12/2019
TP_183 | Transaction table_Eeds deducted | passed | 23/12/2019
TP_184 | Post a service_zero price | passed | 23/12/2019
TP_185 | Transaction History Page_Buy Service with Zero Price | passed | 23/12/2019
TP_186 | Service_Add picture for service | passed | 23/12/2019
TP_187 | Need_Add picture for need | passed | 23/12/2019
TP_188 | Pagination_plugs page | passed | 23/12/2019
TP_189 | Pagination_Messages page | passed | 23/12/2019
TP_190 | Pagination_Transaction page | passed | 23/12/2019
TP_191 | Bidding price_insufficient account balance | passed | 23/12/2019
TP_192 | Bidding price_sufficient account balance | passed | 23/12/2019
TP_193 | No eeds_ buy a service | passed | 23/12/2019
TP_194 | No eeds_ bid a service | passed | 23/12/2019
TP_195 | Buying eeds with credit card_incomplete information or blank | passed | 23/12/2019
TP_196 | Buying eeds with credit card_incorrect information | passed | 23/12/2019
TP_197 | Transaction page_functionality | passed | 23/12/2019
TP_198 | Create Need _Refund % | passed | 23/12/2019
TP_199 | New bid message_owner of the need_no refund% and refund valid | passed | 23/12/2019
TP_200 | Search for a service | passed | 23/12/2019
TP_201 | Search for a need | passed | 23/12/2019
TP_202 | Search by city | passed | 23/12/2019
TP_203 | Verify account_upload government issued id | failed | 23/12/2019 |  | 3 | closed
TP_204 | Verify account_upload government issued id ( NEGATIVE) | passed | 23/12/2019
TP_205 | Verify account_upload government issued id ( NEGATIVE) | passed | 23/12/2019
TP_206 | Warn users about saving the changes when he presses on cancel button (while creating a service / need) | passed | 23/12/2019
TP_207 | Check whether the footer is updated for both App store and Play Store | passed | 23/12/2019
| Execution Summary |  |  | Severity | Number of defects
| Total Testcases | 207 |  | sev 3 | 7
| Executed | 175 |  | sev 4 | 2
| Not Executed/skipped | 32
| Passed (166) | 94%
| Failed (9) | 6%
Defect Summary
| Total | 9
| Open(Reported) | 7
| Closed | 2